## Instructions & Setup
Security Controls Compliance Checklist
How to use & customize this template
1. CUSTOMIZE (fill the yellow cells)
| Parameter | Your value | Notes
| Framework | ISO 27001:2022 | Loads matching control set
| Organization name | Contoso Networks | Header branding
| Assessment date | 2026-07-29 | Report date
| Scoring style | Status + Maturity 1-5 | Yes/No, Maturity, or % complete
| Assessor / owner | H. Jelassi | Default owner value
2. LEGEND
| Green | Implemented
| Amber | Partial
| Red | Not Implemented
| Yellow | Setup cells
3. HOW TO USE
• The first data row is a filled EXAMPLE — overwrite or delete it.
• Yellow cells are meant to be edited. Grey/white cells with formulas update automatically.
• Use the drop-down lists in each column for consistent values.
• Add rows by copying the example row so formatting and drop-downs carry over.

## Checklist
Security Controls Compliance Checklist
Framework control assessment — track status, gaps & remediation
Control ID | Domain | Control Description | Status | Maturity (1-5) | Evidence / Reference | Owner | Gap / Finding | Remediation Action | Target Date
A.5.1 | Organizational | Information security policies defined & approved | Implemented | 5 | ISMS-POL-01 v3 | CISO
A.8.9 | Asset Mgmt | Configuration management baseline enforced | Partial | 3 | CMDB export Q2 | IT Ops | No baseline for branch switches | Extend baseline to branch | 2026-09-30
A.8.16 | Operations | Monitoring & alerting on security events | Implemented | 4 | SIEM dashboards | SOC
A.8.23 | Network Sec | Web filtering / URL control in place | Not Implemented | 1 |  | Network Team | No egress web filtering | Deploy secure web gateway | 2026-11-15
A.8.24 | Cryptography | TLS 1.2+ enforced on public services | Partial | 3 | Scan report 2026-06 | Network Team | 2 legacy endpoints on TLS 1.0 | Upgrade / decommission | 2026-08-31
A.5.30 | Continuity | ICT readiness for business continuity tested | Not Implemented | 2 |  | BCP Lead | No DR test in 12 months | Schedule DR failover test | 2026-10-31
COMPLIANCE SCORECARD
| Total controls | 6
| Implemented | 2
| Partial | 2
| Not Implemented | 2
| % Complete | 33.33%