## Instructions & Setup
Project Deployment / Migration Tracker
How to use & customize this template
1. CUSTOMIZE (fill the yellow cells)
| Parameter | Your value | Notes
| Project name | Core Network Refresh | Header branding
| Project start date | 2026-08-03 | Timeline anchor
| Number of phases | 4 | Prepare / Build / Cutover / Validate
| Team members | H. Jelassi; IT Ops; Network Team; S. Ben Ali | Feeds Owner drop-down
| Include rollback column? | Yes | Shown by default
2. LEGEND
| Green | Done
| Amber | In Progress
| Red | Blocked
| Auto | Variance = Actual − Planned end
| Yellow | Setup cells
3. HOW TO USE
• The first data row is a filled EXAMPLE — overwrite or delete it.
• Yellow cells are meant to be edited. Grey/white cells with formulas update automatically.
• Use the drop-down lists in each column for consistent values.
• Add rows by copying the example row so formatting and drop-downs carry over.

## Deployment Plan
Project Deployment / Migration Tracker
Phased rollout plan — tasks, dates, dependencies & rollback
# | Phase | Task | Owner | Depends On | Planned Start | Planned End | Actual End | Variance (days) | Status | Rollback Step | Notes
1 | 1. Prepare | Design review & sign-off | H. Jelassi | - | 2026-08-03 | 2026-08-07 | 2026-08-07 | 0 | Done | Revert to current design | LLD approved
2 | 1. Prepare | Procure hardware | IT Ops | 1 | 2026-08-10 | 2026-08-21 | 2026-08-24 | 3 | In Progress | Return units | 3-day slip
3 | 2. Build | Rack & stack core switches | Network Team | 2 | 2026-08-25 | 2026-08-28 |  |  | Not Started | Power down & remove | Change window CW-118
4 | 2. Build | Configure & test firewall HA | S. Ben Ali | 3 | 2026-08-31 | 2026-09-04 |  |  | Not Started | Restore prior config | HA pair
5 | 3. Cutover | Migrate VLAN 20 workloads | IT Ops | 4 | 2026-09-07 | 2026-09-08 |  |  | Not Started | Fail back to old core | Maintenance 22:00-02:00
6 | 4. Validate | Post-cutover testing & handover | H. Jelassi | 5 | 2026-09-09 | 2026-09-11 |  |  | Not Started | N/A | Sign-off required
PROGRESS
| Tasks total | 6
| Done | 1
| % Complete | 16.67%